## Project Charter
Visit Us: |  | https://www.otmsite.com
Lean Six Sigma Project Charter
Project No.: |  | 001 | Date: | 2021-05-11 |  | Rev. No.: | 000 |  | Rev. Date: | 2021-05-11
Project Title: |  | OEE Improvement at Assembly Line A |  |  |  | Project Leader: |  | Mr. Jack R.
Process Owner: |  | Mr. Raja R. |  |  |  | Project Sponsor: |  | Mr. Patel P.
Businesss Case: | [5 empty] | Process & Sub Process:
The improvement in OEE by 20% will reduce the manufacturing cost per product by 25% that will improve our profitability by 25% directly. | [5 empty] | Process: Manufacturing Process Sub Process: Assembly Line A
Problem Statement: | [5 empty] | Goal Statement:
The last 4 month's OEE of line A is 45%. So the manufacturing cost of the product is higher | [5 empty] | To Improve the OEE of Line A from the current baseline of 45% to 65% in the next six months. It will give the tangible benefits of 10K USD
Business Matrix: | [5 empty] | Primary Matrix:
Sr No | Description |  | UOM | Base Line | Target | Sr No | Description |  | UOM | Base Line | Target
1 | OEE |  | % | 45 | 65 | 1 | Rate of Availability |  | % | 70 | 82
[6 empty] | 2 | Rate of Performance |  | % | 70 | 80
[6 empty] | 3 | Rate of Quality |  | % | 92 | 99
Project Team: | [5 empty] | Support Personnel:
Name |  |  | Role |  |  | Name |  |  | Role
Boby |  |  | Process Owner |  |  | Piyush |  |  | HR Support
Raju |  |  | Mechanical Mainntenance |  |  | Vihan |  |  | NPD Support
Kamalesh |  |  | Electrical Maintenance
Jyorge |  |  | Tooling Modification
Project Scope: | [5 empty] | Estimated Financial Benefits:
The Project Scope includes only manufacturing assembly line A. All other line excluded from the project | [5 empty] | 10K USD saving in production processing cost saving 5K USD cost saving due to quality rejection on line
Project Start Date: 11-05-2021 | [5 empty] | Estimate Project Completion Date: 30-08-2021
Project Milestones |  | Define |  | Measure |  | Analyse |  | Improve |  | Control
Target Date: |  | 2021-05-20 |  | 2021-06-10 |  | 2021-07-10 |  | 2021-08-10 |  | 2021-08-25
Review Date:
Completion Date:
Approval of the Project Charter
[5 empty] | Name & Signature |  |  |  |  | Date
Project Leader: |  |  |  |  | Mr. Jack R. |  |  |  |  | 2021-05-11
Project Sponsor / Champion: |  |  |  |  | Mr. Patel P. |  |  |  |  | 2021-05-11
Process Owner: |  |  |  |  | Mr. Raja R. |  |  |  |  | 2021-05-11
Financial Advisor: |  |  |  |  | Mr. Harry |  |  |  |  | 2021-05-11